## About
Created on: | 30 Jun 23 17:07 UTC
Jira Site: | https://planning-project-sdv.atlassian.net
Jira Query: | sprint = 27 ORDER BY key ASC, created DESC

## Your Jira Issues
Clé | Résumé | État | Responsable
SDV-396 | powerpoint presentation | Terminé(e) | Charlotte WAEGENEIRE
SDV-397 | project global documentation | Terminé(e) | Charlotte WAEGENEIRE
SDV-401 | api documentation | Terminé(e) | Charlotte WAEGENEIRE
SDV-407 | unitary test categories | Terminé(e) | Charlotte WAEGENEIRE
SDV-408 | unitary test contact | Terminé(e) | Charlotte WAEGENEIRE
SDV-409 | refactor pagination | Terminé(e) | Charlotte WAEGENEIRE
SDV-411 | popup cookies | Terminé(e) | Charlotte WAEGENEIRE
SDV-412 | UI/UX review | Terminé(e) | Charlotte WAEGENEIRE
SDV-417 | sales product and category fix | Terminé(e) | Charlotte WAEGENEIRE
SDV-418 | As a CONNECTED USER, I can cancel a command | Terminé(e) | Charlotte WAEGENEIRE
SDV-421 | As a CONNECTED USER, I can return a product | Terminé(e) | Charlotte WAEGENEIRE
SDV-427 | update doc api & main readme | Terminé(e) | Charlotte WAEGENEIRE
SDV-430 | upload presentation | Terminé(e) | Charlotte WAEGENEIRE
SDV-306 | As a CONNECTED USER, I can see my commands & their status | Terminé(e) | hugo vaillant
SDV-423 | disable users instead of deleting them | Terminé(e) | hugo vaillant
SDV-424 | update info users from backoffice | Terminé(e) | hugo vaillant
SDV-426 | As a CONNECTED USER, I can change my password | Terminé(e) | hugo vaillant
SDV-362 | Carousel Product / do CRUD in the backoffice | Terminé(e) | Tom OLLIVIER
SDV-365 | As an ADMIN, I can add a material (BONUS) | Terminé(e) | Tom OLLIVIER
SDV-366 | As an ADMIN, I can delete a material (BONUS) | Terminé(e) | Tom OLLIVIER
SDV-367 | As an ADMIN, I can modify a material (BONUS) | Terminé(e) | Tom OLLIVIER
SDV-368 | As an ADMIN, I can see all the materials (BONUS) | Terminé(e) | Tom OLLIVIER
SDV-405 | Fix the search filter graphics problem | Terminé(e) | Tom OLLIVIER
SDV-410 | add priority to products | Terminé(e) | Tom OLLIVIER
SDV-425 | Fix delete materials | Terminé(e) | Tom OLLIVIER
SDV-428 | fix price/sale in search page | Terminé(e) | Tom OLLIVIER
SDV-431 | category's name instead of its id in the products table | Terminé(e) | Tom OLLIVIER
SDV-348 | JEST | Terminé(e) | William Wautrin
SDV-394 | Seeds PROD | Terminé(e) | William Wautrin
SDV-399 | Remove -1 quantity from the product as soon as it is ordered | Terminé(e) | William Wautrin
SDV-400 | Technical documentation README | Terminé(e) | William Wautrin
SDV-404 | i18n | Terminé(e) | William Wautrin
SDV-413 | Image & Console bug on admin dashboard | Terminé(e) | William Wautrin
SDV-414 | Resolve compil bug on Mobile project | Terminé(e) | William Wautrin
SDV-415 | README | Terminé(e) | William Wautrin
SDV-416 | Merise / UML use case update | Terminé(e) | William Wautrin
SDV-419 | bug fix | Terminé(e) | William Wautrin
SDV-422 | update uml/mcd/mpd after return product us | Terminé(e) | William Wautrin
SDV-429 | Fix seed | Terminé(e) | William Wautrin