## About
Created on: | 04 Jun 23 20:00 UTC
Jira Site: | https://planning-project-sdv.atlassian.net
Jira Query: | project = SDV AND Sprint = 26 order by created DESC

## Your Jira Issues
Clé | Résumé | État | Responsable
SDV-306 | As a CONNECTED USER, I can see my commands & their status | À faire | hugo vaillant
SDV-399 | Remove -1 quantity from the product as soon as it is ordered | À faire | hugo vaillant
SDV-347 | several materials for a product (BONUS) | À faire | Tom OLLIVIER
SDV-365 | As an ADMIN, I can add a material (BONUS) | À faire | Tom OLLIVIER
SDV-366 | As an ADMIN, I can delete a material (BONUS) | À faire | Tom OLLIVIER
SDV-367 | As an ADMIN, I can modify a material (BONUS) | À faire | Tom OLLIVIER
SDV-368 | As an ADMIN, I can see all the materials (BONUS) | À faire | Tom OLLIVIER
SDV-363 | Security Github patch (Not urgent) | À faire | William Wautrin
SDV-394 | Seeds PROD | À faire | William Wautrin
SDV-362 | Carousel Product / do CRUD in the backoffice | Dev In Progress | Tom OLLIVIER
SDV-348 | JEST | Dev In Progress | William Wautrin
SDV-307 | As a CONNECTED USER, I can access my commands. | Terminé(e) | hugo vaillant
SDV-308 | As a CONNECTED USER, I can see each command’s detail. | Terminé(e) | hugo vaillant
SDV-314 | As a CONNECTED USER, I can enter my delivery address informations. | Terminé(e) | hugo vaillant
SDV-315 | As a CONNECTED USER, I can enter my payment informations. | Terminé(e) | hugo vaillant
SDV-316 | As a CONNECTED USER, I can access my command’s page at the end of the payment. | Terminé(e) | hugo vaillant
SDV-317 | As a USER, I can search a certain product. | Terminé(e) | Tom OLLIVIER
SDV-318 | As a USER, I can order the results. | Terminé(e) | Tom OLLIVIER
SDV-319 | As a USER, I can filter the results. | Terminé(e) | Tom OLLIVIER
SDV-380 | delete product not working and redirecting to admin/contacts/all | Terminé(e) | Tom OLLIVIER
SDV-390 | promotion shouldn't be mandatory | Terminé(e) | Tom OLLIVIER
SDV-340 | As a USER, I can only access the pages I'm allowed to | Terminé(e) | Waegeneire Charlotte
SDV-342 | As an ADMIN, I can select several items for mass actions. | Terminé(e) | Waegeneire Charlotte
SDV-345 | Auth API | Terminé(e) | Waegeneire Charlotte
SDV-383 | admin navbar not closing itself when changing page | Terminé(e) | Waegeneire Charlotte
SDV-385 | URGENT : security breach with session | Terminé(e) | Waegeneire Charlotte
SDV-386 | user session cookies incorrectly set | Terminé(e) | Waegeneire Charlotte
SDV-387 | clean the routes calls for each page | Terminé(e) | Waegeneire Charlotte
SDV-388 | appContext chore | Terminé(e) | Waegeneire Charlotte
SDV-389 | needs to update public routes instead of handling them in getserversideprops | Terminé(e) | Waegeneire Charlotte
SDV-393 | delete product from the homepage if it gets deplaced in the "no category" category | Terminé(e) | Waegeneire Charlotte
SDV-395 | no update or delete "no category" category | Terminé(e) | Waegeneire Charlotte
SDV-403 | restablishing the user on the nav | Terminé(e) | Waegeneire Charlotte
SDV-279 | As an ADMIN, I can check the sales statistics. | Terminé(e) | William Wautrin
SDV-349 | i18n | Terminé(e) | William Wautrin
SDV-359 | Update Promotions into Burger Menu WHEN Promotions filter is done | Terminé(e) | William Wautrin
SDV-361 | UI amelioration | Terminé(e) | William Wautrin
SDV-384 | Take the api calls out of some components and make them in the page | Terminé(e) | William Wautrin