## About
Created on: | 08 May 23 16:16 UTC
Jira Site: | https://planning-project-sdv.atlassian.net
Jira Query: | project = SDV AND Sprint = 25 ORDER BY created DESC

## Your Jira Issues
Clé | Résumé | État | Responsable
SDV-306 | As a CONNECTED USER, I can see my commands. | À faire | hugo vaillant
SDV-307 | As a CONNECTED USER, I can access my commands. | À faire | hugo vaillant
SDV-308 | As a CONNECTED USER, I can see each command’s detail. | À faire | hugo vaillant
SDV-314 | As a CONNECTED USER, I can enter my delivery address informations. | À faire | hugo vaillant
SDV-316 | As a CONNECTED USER, I can access my command’s page at the end of the payment. | À faire | hugo vaillant
SDV-318 | As a USER, I can order the results. | À faire | Tom OLLIVIER
SDV-319 | As a USER, I can filter the results. | À faire | Tom OLLIVIER
SDV-342 | As an ADMIN, I can select several items for mass actions. | À faire | Waegeneire Charlotte
SDV-347 | several materials for a product (BONUS) | À faire | Tom OLLIVIER
SDV-361 | UI amelioration | À faire | William Wautrin
SDV-315 | As a CONNECTED USER, I can enter my payment informations. | Dev In Progress | hugo vaillant
SDV-317 | As a USER, I can search a certain product. | Dev In Progress | Tom OLLIVIER
SDV-340 | As a USER, I can only access the pages I'm allowed to | Dev In Progress | Waegeneire Charlotte
SDV-345 | Auth API | Dev In Progress | Waegeneire Charlotte
SDV-383 | admin navbar not closing itself when changing page | Dev In Progress | Waegeneire Charlotte
SDV-385 | URGENT : security breach in the appcontext | Dev In Progress | Waegeneire Charlotte
SDV-386 | user session cookies incorrectly set | Dev In Progress | Waegeneire Charlotte
SDV-387 | clean the routes calls for each page | Dev In Progress | Waegeneire Charlotte
SDV-388 | appContext chore | Dev In Progress | Waegeneire Charlotte
SDV-380 | delete product not working and redirecting to admin/contacts/all | Pending Merge | Tom OLLIVIER
SDV-295 | As a USER, I can delete an item in my cart. | Terminé(e) | William Wautrin
SDV-296 | As a USER, I can update an item in my cart. | Terminé(e) | William Wautrin
SDV-297 | As a USER, I can check my cart. | Terminé(e) | William Wautrin
SDV-298 | As a USER, I can see a category’s products. | Terminé(e) | Waegeneire Charlotte
SDV-299 | As a USER, I can see a product’s details | Terminé(e) | Tom OLLIVIER
SDV-300 | As a USER, I can add the product to my cart | Terminé(e) | William Wautrin
SDV-301 | As a USER, I can see similar products. | Terminé(e) | Tom OLLIVIER
SDV-320 | As a USER, I can change my password | Terminé(e) | hugo vaillant
SDV-321 | As a USER, I can ask for a new password. | Terminé(e) | hugo vaillant
SDV-323 | As a USER, I can go to each displayed product’s page. | Terminé(e) | William Wautrin
SDV-324 | As a USER, I can go to the displayed carrousel’s slide page. | Terminé(e) | William Wautrin
SDV-325 | As a USER, I can go to each displayed category’s page. | Terminé(e) | William Wautrin
SDV-327 | As a USER, I can use the burger menu. | Terminé(e) | William Wautrin
SDV-328 | As a USER, I can use the navbar. | Terminé(e) | William Wautrin
SDV-329 | As a USER, I can use the footer at the end of every page. | Terminé(e) | William Wautrin
SDV-338 | As an ADMIN, I can order the items of a section by a column. | Terminé(e) | hugo vaillant
SDV-346 | As an USER, I can see all the categories (bonus) | Terminé(e) | Waegeneire Charlotte
SDV-353 | As a CONNECTED USER, I can log out. | Terminé(e) | William Wautrin
SDV-354 | Setup React Native | Terminé(e) | William Wautrin
SDV-355 | As a USER, I can see a few products on sales on the homepage. (BONUS) | Terminé(e) | Waegeneire Charlotte
SDV-358 | Knex seeds | Terminé(e) | William Wautrin
SDV-360 | Admin Navbar not displaying to bottom | Terminé(e) | William Wautrin
SDV-364 | Exemple i18n / JEST e2e | Terminé(e) | William Wautrin
SDV-369 | Error Message in Login if credentials are false | Terminé(e) | William Wautrin
SDV-371 | Headers problem on the signup page when already logged in | Terminé(e) | William Wautrin
SDV-372 | Impossible to create a cart if not logged in | Terminé(e) | William Wautrin
SDV-374 | Add redirection to settings of account in Admin Navbar | Terminé(e) | William Wautrin
SDV-375 | Responsive Homepage Admin | Terminé(e) | William Wautrin
SDV-376 | NeonDB + Vercel | Terminé(e) | William Wautrin
SDV-377 | logging out the user when the account is deleted | Terminé(e) | William Wautrin